## BLANK - Work Log
WORK LOG FOR THE PROJECT
NAME | CONTACT
Lan Dinh | 672-866-0515
DEPARTMENT | SUPERVISOR |  |  |  | TOTAL TIME ON SCHEDULE
Complete non-shaded cells only. Shaded cells populate automatically.
ACTIVITY | DATE | START TIME | END TIME | TOTAL TIME | STATUS | NOTES
Doing Interest and Expertise Survey to find out what skills and rechnologies want to work on | 2025-01-12 | 17:00 | 18:00 | 1:00 | Complete
Finding the topic for the research project, looking for paper researches and prvious works | 2025-01-14 | 17:00 | 19:00 | 2:00 | Complete
Creating and adding the Client in the Repo |  | 9:00 | 9:00 | 0:00 | Complete
Writing the draft proposal for the Client | 2025-01-20 | 9:00 | 15:00 | 6:00 | Complete
Discussing to the Client about the choosing topic is Activity Reminder Mobile App for Douglas College students | 2025-01-23 | 10:00 | 10:30 | 0:30 | Complete
Changing the topic to the Dashboard Development by Python for analyzing movie trneds and insights | 2025-01-24 | 10:00 | 10:30 | 0:30 | Approved
Rewriting the proposal | 2025-01-24 | 13:00 | 20:00 | 7:00 | Complete
Cleaning database (Netflix database) | 2025-01-26 | 13:00 | 15:00 | 2:00 | Complete
Writing the Progress Report | 2025-01-29 |  |  | 0:00 | In Progress
Writing questions for an interview | 2025-02-01 | 16:00 | 17:00 |  | In Progress
Drafting the ideas cho the dahsboard | 2025-02-02 | 17:00 | 18:00 | 1:00 | In Progress
Coding for the dashboard by Python | 2025-02-06 | 13:00 | 23:00 | 10:00 | In Progress
0:00
0:00

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold
Other 1
Other 2